## E.1 Starting Up a Project
E.1 Starting up a Project
Question | Yes/No
1 Have project management team roles been allocated for the:
a Executive?
b Project Manager?
c Senior User(s)?
d Senior Supplier(s) – if appropriate at this point?
e Project Support?
f Team Managers – if appropriate at this point?
g Project Assurance?
h Change Authority – if appropriate at this point?
2 Do the Project Board members have sufficient authority, availability and credibility to direct the project?
3 Are the project’s stakeholders sufficiently represented by the Project Board?
4 Do role descriptions exist for each key appointment?
5 Have those people appointed confirmed their acceptance?
6 Has a Daily Log been set up?
7 Has the Lessons Log been set up?
8 Have lessons from previous similar projects been identified and, where appropriate, applied?
9 If the organization has not undertaken a project like this before, have lessons been sought from comparable projects external to the organization?
10 Has the Project Brief been produced?
11 Is there an outline Business Case?
12 Has the Project Product Description been produced?
13 Has the project approach been decided upon?
14 Is there a Stage Plan for the initiation stage?

## E.2 Directing a Project
E.2 Directing a Project
E.2.1 Authorize initiation
Question | Yes/No
15 Has the Project Board approved the Project Brief? Specifically, has it:
■ Confirmed the project definition and approach?
■ Reviewed and approved the Project Product Description?
■ Formally confirmed the appointments to the core project management team?
■ Reviewed and approved the outline Business Case, particularly the projected benefits?
16 Has the Project Board approved the Initiation Stage Plan? Specifically, has it:
■ Approved the plan to develop the Project Initiation Documentation?
■ Obtained or committed the resources needed by the Stage Plan for the initiation stage?
■ Ensured that adequate reporting and control mechanisms are in place for the initiation stage?
■ Set tolerances for the initiation stage?
■ Requested the necessary logistical support (for example, accommodation, communication facilities, equipment and any Project Support) from corporate or programme management?
■ Confirmed that they have understood any risks that affect the decision to authorize the initiation stage?
■ Confirmed to the Project Manager that the work defined in the Initiation Stage Plan may start?
17 Has the Project Board informed corporate or programme management (and other interested parties) that project initiation has been authorized?
E.2.2 Authorize the project
Question | Yes/No
18 Has the Project Board approved the Project Initiation Documentation? Specifically, has it:
■ Confirmed that the Business Case is viable, desirable and achievable and meets corporate or
programme management expectations and standards, and approved it?
■ Confirmed that lessons from previous similar projects have been reviewed and incorporated?
■ Confirmed that the Quality Management Strategy will deliver the quality expectations, and approved it?
■ Confirmed that that the Configuration Management Strategy will deliver the approach expected, and approved it?
■ Confirmed that that the Risk Management Strategy will safeguard the project, and approved it?
■ Confirmed that there has been a risk assessment, and that risk response actions have been planned?
■ Confirmed the validity and achievability of the Project Plan and approved it?
■ Confirmed that the Benefits Review Plan covers all expected benefits, and approved it?
■ Confirmed that all members of the project management team have agreed their roles (the project management team structure, roles and responsibilities)?
■ Ensured that the project controls are adequate for the nature of the project?
■ Ensured that the information needs and timing of communications, as defined in the Communication Management Strategy, are adequate for the nature of the project, and approved it?
■ Reviewed the tolerances for the project provided by corporate or programme management to ensure that they are appropriate and realistic?
■ Considered the consistency of the various components and approved the Project Initiation Documentation overall?
19 Has the Project Board informed corporate or programme management (and other interested parties) that the project has been authorized?
E.2.3 Authorize a Stage or Exception Plan
Question | Yes/No
20 Has the Project Board reviewed the End Stage Report? Specifically:
■ Did the board review the performance status of the project using the End Stage Report for the current management stage?
■ Has the board reviewed the benefits achieved and lessons learned during the stage?
21 Has the Project Board assessed overall project viability? Specifically, has it:
■ Reviewed the Project Plan and the position in relation to project tolerances agreed with corporate or programme management?
■ Reviewed the Business Case to ensure that the project is still justified?
■ Reviewed the key risks to ensure that the exposure level is still acceptable and that response actions are planned?
■ Obtained decisions from outside the project for any potential deviations beyond project tolerances? (For example, if this project is part of a programme, then programme management should have examined the impact on the programme, and taken appropriate action.)
22 Has the Project Board reviewed and approved the next Stage Plan (or Exception Plan)? Specifically, has it:
■ Reviewed the plan for which the Project Manager is seeking approval? (This will be a Stage Plan for the next management stage or an Exception Plan.)
■ Authorized the Project Manager to proceed with the submitted plan (Stage Plan or Exception Plan) or instructed the Project Manager to prematurely close the project?
■ Set the tolerances for the next management stage or (in the case of an Exception Plan) revised the current stage tolerances as necessary?
23 Has the Project Board informed corporate or programme management (and other interested parties) that the next stage has been authorized (or an exception plan for the current stage has been approved)?
E.2.4 Give ad hoc direction
Question | Yes/No
24 Has the Project Board responded to the Project Manager’s requests? Specifically, has it:
■ Reviewed the request? (This could be informal or formal, the latter in the form of an Issue Report.)
■ Made a decision – for example, approved, rejected, deferred decision, requested more information?
■ Provided guidance to the Project Manager?
25 Has the Project Board responded to reports? Specifically, has it:
■ Reviewed the latest Highlight Report in order to understand the status of the project and satisfied itself, through a dialogue with the Project Manager, that the stage is progressing according to plan?
■ Made decisions on Exception Reports – adjusted tolerances or approved responses to the exception as appropriate?
■ Made decisions on Issue Reports within the board’s delegated limits of authority or sought advice from corporate or programme management?
26 Has the Project Board responded to external influences? Specifically, has it:
■ Ensured that the project is kept informed of external events that may affect it?
■ Ensured that the project remains focused on the corporate or programme objectives set, and remains justified in business terms?
■ Ensured that the Project Manager is notified of any changes in the corporate or programme environment that may impact on the project and that appropriate action is taken?
27 Has the Project Board informed corporate or programme management (and other interested parties) of the project’s progress in accordance with the Communication Management Strategy?
E.2.5 Authorize project closure
Question | Yes/No
28 Has the Project Board confirmed handover and acceptance? Specifically, has it:
■ Verified that the handover of the project product was in accordance with the Configuration Management Strategy and in particular that records of all required user acceptance and operational/maintenance acceptance exist?
■ Ensured that, where appropriate, the resulting changes in the business are supported and sustainable?
■ Ensured that any customer quality expectations that cannot be confirmed until after the project closes (e.g. performance levels regarding reliability) are included in the Benefits Review Plan as a post-project check?
29 Has the Project Board Approved the End Project Report? Specifically, has it:
■ Used the version of the Project Initiation Documentation which was approved at project initiation as the baseline to assess how the project has deviated from its initial basis, and to provide information against which the success of the project can be judged?
■ Ensured follow-on action recommendations have been recorded correctly in the End Project Report and that the appropriate groups have been made aware of their responsibility for taking them forward?
■ Approved the End Project Report for distribution to any interested parties, such as corporate or programme management?
30 Has the Project Board reviewed the Lessons Report and agreed who should receive it? Has the Board ensured that the appropriate groups (for example, corporate or programme management, centre of excellence) have been made aware of their responsibility for taking any recommendations forward?
31 Has the Project Board confirmed the Business Case? Specifically, has it confirmed the updated Business Case by comparing actual and forecast benefits, costs and risks against the approved Business Case within the Project Initiation Documentation? (It may not be possible to confirm all the benefits as some will not be realized until after the project is closed.)
32 Has the Project Board approved the updated Benefits Review Plan? Specifically, has it:
■ Reviewed and gained approval for the updated Benefits Review Plan, ensuring that it addresses the expected benefits that cannot yet be confirmed?
■ Confirmed that the responsibility for the Benefits Review Plan has been transferred to corporate or programme management?
33 Has the Project Board issued the project closure notification? Specifically, has it:
■ Reviewed and issued a project closure notification in accordance with the Communication Management Strategy?
■ Advised those who have provided the support infrastructure and resources for the project that these can now be withdrawn?
■ Released the resources provided to the project?
■ Provided a closing date for costs being charged to the project?

## E.3 Initiating a Project
E.3 Initiating a Project
Question | Yes/No
34 Have lessons from previous similar projects been identified and, where appropriate, have they been applied?
35 Has the Risk Management Strategy been defined and documented?
36 Has the Risk Register been set up and populated?
37 Has the Configuration Management Strategy been defined and documented?
38 Have the initial Configuration Item Records been set up?
39 Has the Issue Register been set up and populated?
40 Has the Quality Management Strategy been defined and documented?
41 Has the Quality Register been set up and populated?
42 Has the Communication Management Strategy been defined and documented?
43 Have the project controls been determined and established?
44 Has the Project Plan been created?
45 Has the project management team structure been updated to reflect any new roles being appointed or any changes to responsibilities of existing roles?
46 For new appointments, do role descriptions exist and have those people who have been appointed confirmed their acceptance?
47 Has the outline Business Case been refined into a detailed Business Case?
48 Has the Benefits Review Plan been created (this may have been done by corporate or programme management)?
49 Has the Project Initiation Documentation been assembled?

## E.4 Controlling a Stage
E.4 Controlling a Stage
Question | Yes/No
50 Have Work Packages been created and issued?
51 Have all the Team Managers agreed all their Work Packages?
52 Have completed products been produced in accordance with the Work Package and Product Description?
53 Have the relevant Configuration Item Records been created/updated?
54 Has the Quality Register been maintained?
55 Were any products handed over as part of a phased delivery? If so, were they handed over in accordance with the Configuration Management Strategy?
56 Has the Risk Register been maintained?
57 Has the Issue Register been maintained?
58 Has the Stage Plan been updated with actuals and revised forecasts?
59 Has the Daily Log been maintained?
60 Have Checkpoint Reports been received for each issued Work Package at the frequency and in the format agreed?
61 Was progress (actual and forecast) checked against agreed tolerances?
62 If tolerances were forecast to be exceeded, were they escalated to the Project Board?
63 If corrective actions were required, were they logged, implemented and tracked?
64 Was the Business Case periodically checked for ongoing viability?
65 Were Highlight Reports created and issued in accordance with the agreed reporting format and frequency?
66 Do Issue Reports exist for all issues being handled formally?
67 Do Exception Reports exist for all exceptions raised to the Project Board?
68 Has the Lessons Log been updated with any new lessons?

## E.5 Managing Product Delivery
E.5 Managing Product Delivery
Question | Yes/No
69 Did the Work Package and Product Description(s) contain sufficient information, including crossreferences, to enable the Team Manager to produce the products required?
70 Has a Team Plan been created that demonstrates that the Work Package could be completed within agreed tolerances?
71 Has the Team Plan been updated with actuals and revised forecasts?
72 Was progress (actual and forecast) checked against agreed tolerances?
73 If tolerances were forecast to be exceeded, were they escalated to the Project Manager?
74 Were Checkpoint Reports issued to the Project Manager at the frequency and in the format agreed?
75 Did the Team Manager notify the Project Manager of any issues and risks?
76 Do approval records exist for each completed product?
77 Did the Team Manager notify Project Support of any required updates to Configuration Item Records and the Quality Register?
78 Did the Team Manager notify the Project Manager that all the products in the Work Package had been delivered?

## E.6 Managing a Stage Boundary
E.6 Managing a Stage Boundary
Question | Yes/No
79 Have all products that were planned to be completed within the stage been approved?
80 Has a Product Status Account been created to verify the status of the stage’s products?
81 If there was a product handover during the stage, were related outstanding issues documented as follow-on action recommendations ready for distribution subject to Project Board approval?
82 Has the Lessons Log been reviewed and updated?
83 If required, has a Lessons Report been created ready for distribution, subject to Project Board approval?
84 Has the Stage Plan been updated with actuals?
85 Has the Risk Management Strategy been reviewed and (if necessary) updated?
86 Has the Risk Register been reviewed and updated?
87 Has the Configuration Management Strategy been reviewed and (if necessary) updated?
88 Have the Configuration Item Records been reviewed and updated?
89 Has the Issue Register been reviewed and updated?
90 Has the Quality Management Strategy been reviewed and (if necessary) updated?
91 Has the Quality Register been reviewed and updated?
92 Has the Communication Management Strategy been reviewed and (if necessary) updated?
93 Have the project controls been reviewed and (if necessary) updated?
94 Has the Project Plan been reviewed and (if necessary) updated?
95 Has the project management team structure been updated to reflect any new roles being appointed or any changes to responsibilities of existing roles?
96 For new appointments, do role descriptions exist and have those people who have been appointed confirmed their acceptance?
97 Has the Business Case been reviewed and (if necessary) updated?
98 Has the Benefits Review Plan been reviewed and (if necessary) updated?
99 Has the Project Initiation Documentation been reviewed and (if necessary) updated?
100 Has an End Stage Report been produced showing actual against planned performance, and summarizing lessons and follow-on action recommendations?
101 Has the End Stage Report been issued to the Project Board in accordance with the project controls?
For the next stage
102 Has a Stage Plan for the next stage been created?
103 Have Product Descriptions been created for the next stage’s products?
104 Has the Project Board been requested to authorize the next stage?
For exceptions
105 Has an Exception Plan been created (if requested by the Project Board)?
106 Have Product Descriptions been created/updated for the Exception Plan?
107 Has the Project Board been requested to approve the Exception Plan?

## E.7 Closing a Project
E.7 Closing a Project
Question | Yes/No
108 Have all products been completed and approved?
109 Has a Product Status Account been created to verify the status of all the products?
110 Have all outstanding issues been documented as follow-on action recommendations ready for distribution subject to Project Board approval?
111 For premature closure, has the means for recovering products that have been completed or are in progress been approved by the Project Board? If requested, was an Exception Plan created and approved?
112 Is there an acceptance record for the handover of the project product?
113 Does the acceptance record include operational and maintenance acceptance?
114 Has the Lessons Log been reviewed and a Lessons Report created ready for distribution subject to Project Board approval?
115 Has the Project Plan been updated with actuals?
116 Has the Business Case been updated with actuals?
117 Has the Benefits Review Plan been updated with actuals?
118 Has an End Project Report been produced showing actual against planned performance and summarizing lessons and follow-on action recommendations?
119 Has the End Project Report been issued to the Project Board in accordance with the project controls?
120 Has a draft project closure notification been created for Project Board approval and onward distribution?
121 Have all registers and logs been closed?
122 Has all project documentation been archived?