FOR IMMEDIATE RELEASE

Contacts:

| Daniela Karthaus |  |  | Francesca Buckley |
| --- | --- | --- | --- |
| Hitachi Rail Europe |  |  | Hitachi Rail Europe |
| +44 (0)7920 205 631 |  |  | +44 (0)7710 915412 |
| Daniela.karthaus@hitachirail-eu.com |  |  | Francesca.buckley@hitachirail-eu.com |

Hitachi Rail Europe celebrates topping out at new Stoke Gifford Train Maintenance Centre

Stoke Gifford, 23 January, 2015 – Hitachi Rail Europe Ltd. today celebrated the completion of the external building envelope at its Stoke Gifford Train Maintenance Centre currently under construction in South Gloucestershire, near Bristol.

The brand-new facility will support and maintain the Class 800/801 trains the company is delivering through Agility Trains for the Department for Transport’s £5.7bn Intercity Express Programme (IEP). These trains will be running on the Great Western Main Line from 2017.

This celebration represents a significant milestone in the £80 million development of the site, which started in August 2013 and is scheduled to be completed by the end of the year. Now that the external building envelope is complete, moving forwards all work will focus on the interior fit –out of the facility.

The ceremony was hosted by Andy Barr, Chief Operating Officer (COO) at Hitachi Rail Europe and Paul Lilley, Contracts Manager, VolkerFitzpatrick, with representatives of the Department for Transport and local government in attendance.

During the event, guests were given a breakdown of the work currently underway at the site and were invited to observe the progress that had so far been made in the construction process.

Rail Minister Claire Perry said: “We are investing record amounts building a world-class railway as part of our long term economic plan. Hitachi’s new InterCity Express trains will provide more seats, more services and better journeys for passengers, transforming train travel for thousands along the Great Western Main Line.

“I congratulate Hitachi for making the investment, which will ensure that these new trains are maintained to the highest standard. Along with the decision to build the trains in the UK, this is great news for our economy.”

Andy Barr, COO of Hitachi Rail Europe, said: “Today’s event marks a key development in the build progress at our Stoke Gifford Train Maintenance Facility. Tasked with housing and maintaining the Class 800/801 Great Western Main Line fleet, it will play a crucial role in ensuring our rolling stock delivers the optimum level of service to passengers on the route. I can’t emphasise enough how much we value the hard work of VolkerFitzpatrick and the local supply chain in delivering this ground-breaking facility.”

Once completed, the state-of-the-art depot will comprise a maintenance building, office and staff accommodation space, stabling and servicing roads, and a carriage wash machine.

Paul Lilley, Contracts Manager for VolkerFitzpatrick said: “We are very proud to have been awarded the contracts to build three rail depots for Hitachi Rail Europe. By working in collaboration with Hitachi Rail Europe, stakeholders and our supply chain we can demonstrate the one team approach that is critical in the successful delivery of these rail depot projects.

“VolkerFitzpatrick made a commitment to engage with the community during the construction phase to help Hitachi build on a legacy for the coming 27 years. We are continuously engaging with local schools and colleges, providing work experience, apprenticeships and site visit opportunities. VolkerFitzpatrick also received the status as a National Skills Academy for Construction, delivered by the Construction Industry Training Board (CITB) and the Stoke Gifford project is praised as best practice in the construction industry by receiving one of the highest Considerate Constructors Scheme scores in the UK.

“We look forward to spreading our success and close collaboration to ensure there is a lasting legacy of support when the construction works are completed.”

- Ends -

Key facts about the construction process so far:

- 1406 Foundation Piles to Maintenance Building - completed May 14

- Foundation Pile Caps and Tie Beams – completed June 14

- Erection of Structural Steelwork – 450 tonnes in 7 weeks, completed mid-July 2014

- Sheet Piling to Equipment Drops – completed mid-June 2014

- Bulk Earthworks to date – 389,931m3

- Construction of New Culvert – complete Jan 2015

- Wheel lathe building – Piles, steelwork, cladding completed Dec 14

- Connection into parkway – completed November 2014

- CET Slabs – completed December 2014

About Hitachi, Ltd.

Hitachi, Ltd. (TSE: 6501), headquartered in Tokyo, Japan, delivers innovations that answer society’s challenges with our talented team and proven experience in global markets. The company’s consolidated revenues for fiscal 2013 (ended March 31, 2014) totaled 9,616 billion yen ($93.4 billion). Hitachi is focusing more than ever on the Social Innovation Business, which includes infrastructure systems, information & telecommunication systems, power systems, construction machinery, high functional materials & components, automotive systems, healthcare and others. For more information on Hitachi, please visit the company's website at http://www.hitachi.com.

About Hitachi Rail Europe Ltd.

Hitachi Rail Europe Ltd., is a wholly owned subsidiary of Hitachi Europe, Ltd. and is headquartered in London, UK.
Hitachi Rail Europe is a total railway system supplier offering rolling stock, traction equipment, signalling, traffic management systems, and maintenance depots.
Hitachi draws on many years of experience as a leading supplier of high-speed trains such as the Shinkansen (bullet train) for the Japanese and international markets. In Europe, Hitachi Rail Europe’s first rolling stock contract was to deliver a fleet of 29 Class 395 trains, the first domestic high-speed train in the UK, which are maintained at Hitachi’s state of the art depot in Ashford, Kent. As part of the British Department for Transport’s Intercity Express Programme, Hitachi Rail Europe will replace the UK’s ageing fleet of Intercity trains, and will establish a new rolling stock manufacturing facility in Newton Aycliffe, UK for this purpose. The trains will be maintained and serviced in a number of new maintenance depots along the Great Western Main Line and the East Coast Main Line.

# # #